## devs
name | link | notes
Petar B | https://www.upwork.com/freelancers/~01fad5b59e56e2df55/ | good ratings and reviews. GIS expert. Not too expensive.
more here: | https://www.upwork.com/hire/r-shiny-freelancers/

## task_list
id | issue | importance | who | description | notes
| csv imports validation | essential | justin? | add validation rules on csv import and warn user if csv does not meet requirements e.g. na values, no latitude and longitude fields, numbers out of range. We will supply the rules. | very fussy at the moment, must be lat long csv.
| reset button | essential |  | to clear the map and all data values i.e. refresh and start again | Should be easy to set to NULL
| gbif import | essential | steve | module to import data from GBIF (partially working) | just needs to interact with csv points loaded separately
| conditional panel for gbif and csv points | essential |  | when user adds csv file or gbif points, a new switch button will appear. this allows the user to switch on/off the gbif or csv points
| merge csv and gbif points for analysis | essential | baz? | analysis should be made on either just gbif, just user csv or both | this is how it works in geocat. Should we have a template format that we merge GBIF and imported csv files?
| user can start an empty assessment with no WCVP name | essential |  | when user selects a blank assessment i.e .no name selection- the species name is blank, but user can add
| download results in SIS connect format | essential | steve | csv download with EOO results and category as well as country codes and any other basic info | as per Rapid LC, but note that some csv standards have changed from IUCN - files zipped
| download cleaned points file | essential |  | csv download in various formats including IUCN format | i think we have this mapped already, but note updated file standards. GBIF only is easy, but merged with csv is harder
| help pages | essential | steve | for Kew team to add
| click on map markers to get metadata | essential |  | user can click a point marker on the map e.g. collector name. | should be easy in leaflet
| tests! | essential |  | check that we haven't broken anything when updating
| acessibility | essential |  | Needs to meet Web Content Accessibility Guidelines (WCAG) 2.1 at the AA standard | https://github.com/ewenme/shinya11y; https://educationshinyappteam.github.io/Style_Guide/accessibility.html
| user added points | nice to have |  | user can add points directly to the map with point and click | suggest add to the csv
| user point editing | nice to have |  | user can edit i.e. move a point, or delete it and this is updated in the table (flagged if moved?) | suggest add to the csv
| map and table linkage | nice to have |  | user can filter the table and this can be displayed in the map - vice versa | see here for example
| table editing | nice to have |  | user can edit the table e.g. adjust lat long | suggest edit csv and reload - if we make that bit mega easy then shouldn;t be too much of a burden, but dynamic editing would be nice
| display AOO cells | nice to have | justin? | as per geocat - display when analysis button is switched on | only points and convex hull at the moment
| add TDWG native range map | nice to have |  | using WCVP TDWG level 3 - display automatically | use function from new WCVP package?
| batch analysis | nice to have |  |  | need some though, but see rapid LC
| styling | nice to have |  | try to emulate geocat theme with 'darkly' shinythemes or similar | darkly not workin for some reason
| data cleaning | nice to have |  | coordinate cleaner options to apply to point data and native range clipper
| aoh analysis | nice to have |  | for later on…
| rapidLC anaysis | nice to have |  | display if likely to be threatened or not - number of points, number of TDWG
| prediction model? | nice to have |  | Quick and dirty SDM? Simplified from Shiny biomod workflow.
| add IUCN ratings | nice to have |  | IUCN rating icons to match EOO and AOO values
| logfile | nice to have |  | records settings and decisions made during session e.g. cleaning steps,

## job description
Shiny app developer to move demo app to deployment | £ | $
| 4219 | 5500
Try a small task for a small amount and see how it works out - if ok, we add more tasks
Code open source - updates through github - steve's?
Previous version: http://geocat.kew.org/
Needs to meet Web Content Accessibility Guidelines (WCAG) 2.1 at the AA standard
Currently being hosted on shiny https://spbachman.shinyapps.io/geocat_staging/
https://github.com/stevenpbachman/geocat_staging
d001141 (steve desktop) C:\geocat_staging

## end of life notice
GeoCAT holding text for redirect
Important news on the future of GeoCAT
Dear GeoCAT users, we regret to inform you that due to a combination of factors, GeoCAT is getting close to the end of its life. Firstly, GeoCAT was developed by the Royal Botanic Gardens, Kew and is therefore subject to compliance with UK legislation on website accessibility (Public Sector Bodies [Websites and Mobile Applications] Accessibility Regulations 2018, which aligns with Web Content Accessibility Guidelines (WCAG) 2.1 at the AA standard). Unfortunately the site fails to meet these standards. Secondly, GeoCAT dates back to 2011 (check this?!) and is therefore sitting on some old technology and services. This is likely the reason why GeoCAT has been going temporarily offline more often in recent years. We currently do not have sufficient resources to address these issues in the short term and therefore expect to be closing down GeoCAT at some point in the following 6(?) months.
We have already moved across the algorithms used in GeoCAT to the R programming language (see the rCAT package - https://cran.r-project.org/web/packages/rCAT/). However, we appreciate that many users may prefer to use an interface and have therefore developed a preliminary shiny web application here (https://spbachman.shinyapps.io/geocat_staging/).
Please note that this application is still in development. We hope to provide a more stable solution in the future, subject to funding, but welcome feedback on ways to improve this version.